## Project Planner
[7 empty] | Actual Start |  |  |  |  | Actual Duration
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | Milestone 1 |  |  |  |  | Milestone 2 |  |  |  |  | Milestone 3
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Create Offline Storage for JSON Data Files | 11 | 1 | 10 | 1
Create Graphs from JSON Data Files | 11 | 2 | 10
Create Express API with Cookies | 12 | 1
Create MongoDB | 13 | 1
Link Express API with MongoDB | 13 | 1

## 1
Actual Start
Actual Duration
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | Milestone 1 |  |  |  |  | Milestone 2 |  |  |  |  | Milestone 3
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Display a Note Pressed on Terminal | 1 | 1 | 1 | 1
Display Graphical Shapes | 1 | 1 | 1 | 1
Keyboard Input Manipulates Shapes | 1 | 1 | 1 | 1
Display what Key been Pressed | 1 | 1 | 1 | 1
Display Keyboard Graphically | 1 | 1 | 1 | 1
Keyboard Input Displays Note Press on Graphical Keyboard | 1 | 1 | 1 | 1
Display Multiple Notes Pressed on Graphical Keyboard | 1 | 1 | 1 | 2
Graphical Keyboard Resizes to Canvas Size | 2 | 1 | 2 | 1
Create Music Sheet Outline | 2 | 1 | 2 | 1
Create Shape on Music Sheet when Note Presed | 2 | 1 | 2 | 1
Display Multiple Notes Pressed on Music Sheet | 3 | 1 | 3 | 1
Produce Tone on Key Press (On and Off) | 4 | 1 | 4 | 1
Produce Specific Note Tone on Key Press | 4 | 1 | 4 | 1
Animated Note Moves Across Music Sheet and Repeats | 4 | 1 | 4 | 1
Note Repeats to a Different Line/Note | 4 | 1 | 4 | 1
Display More than One Note at a Time on Music Sheet | 4 | 1 | 4 | 1
Press Key at Specific Time to Raise Count | 5 | 1 | 5 | 1
Ability to Change Speed of Note | 5 | 1 | 5 | 1

## 2
[7 empty] | Actual Start |  |  |  |  | Actual Duration
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | Milestone 1 |  |  |  |  | Milestone 2 |  |  |  |  | Milestone 3
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Create Level System | 6 | 1 | 6 | 1
Create Level 1 | 6 | 1 | 6 | 1
Create Level 2 | 7 | 1 | 6 | 1
Create Level 3 | 7 | 1 | 6 | 1
Create Level 4 | 7 | 1 | 7 | 1
Create Level 5 | 8 | 1 | 7 | 1
Create Level 6 | 8 | 1 | 7 | 1
Create Level 7 | 8 | 1 | 8 | 1
Create Level 8 | 8 | 1 | 8 | 1
Create Level 9 | 9 | 1 | 8 | 1
Create Level 10 | 9 | 1 | 8 | 1
Create Level 11 | 9 | 1 | 8 | 1
Create Level 12 | 9 | 1 | 8 | 1
Create Level 13 | 9 | 1 | 8 | 1
Create Level 14 | 9 | 1 | 8 | 1
Create Data Capture | 10 | 1 | 8 | 1
Change Levelling system | 10 | 1 | 9 | 1
Create Level 15 | 10 | 1 | 9 | 1